## Sheet1
Sub-Package | Total | PO Released | Remark | MFC DONE | Remark | Delivered | Partially Delivered | Approved - Await. PO/Disp. | In Progress (PO/Dispatch) | In Progress | Pending Approval | Not Started | Cancelled/ Rejected | % Complete | Remark
Electrical (DC Building) | 36 | 32 | Rest 5 Nos PO related to Fire sealant & Acnchor fastner etc. | 25 | 6 Nos are final light fixtures. 5 Nos will required after 6 months | 8 | 4 | 0 | 0 | 0 | 1 | 1 | 100% | 0.33333
GIS - 220kV Substation | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
ELECTRICAL | 36 | 32 |  | 25 |  | 8 | 4 | 0 | 0 | 0 | 1 | 1 | 1 | 0.33333
HVAC | 74 | 61 | Rest 13 Nos of PO will be released within 2 weeks | 14 | 23 Nos shop drawings Approved as noted to be approved.Space concern for delivery of material. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
PHE | 28 | 25 | Rest 3 Nos are very short Lead items | 10 | 5 Nos will require after 4-6 months.74 Nos shop drawings Approved as noted to be approved.Space concern for delivery of material. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
FPS | 77 | 72 |  | 10 | 21 Nos out of 56 Nos shop drawings Approved as noted to be approved.Space concern for delivery of material. | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0.012987
ELV | 168 | 151 | Rest 17 Nos of PO will be released within September End | 7 | 75 Nos shop drawings Approved as noted to be approved.Space concern for delivery of material. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
HSD | 31 | 31 |  | 1 | FPU & Decanting unit TDS with P & ID has been finalized on 16/09/2026 – All drawings shall be completed 30/09/2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
Telecom | 77 | 70 |  | 49 |  | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sheet2
Package description | Total drawings | Total drawings submitted to TPL by Micron | Pending with TPL for Submisison to JEG | Submission to JEG by TPL | Approved | Approved as Noted | Under review | Revise & Resubmit-R0 | Revise & Resubmit-R1 | Revise & Resubmit-R2 | Revise & Resubmit-R3 | Revise & Resubmit-R4 | Revise & Resubmit-R5 | Revise & Resubmit-R6 | Yet to submit by Micron | CODE B to CODE A Approval (Under review)
ELECTRICAL | 384 | 357 | 0 | 357 | 34 | 264 | 20 | 22 | 9 | 3 | 5 | 0 | 0 | 0 | 27 | 47
HVAC | 157 | 98 | 0 | 98 | 0 | 23 | 3 | 7 | 43 | 22 |  |  |  |  | 59
FIRE | 56 | 56 | 0 | 56 | 2 | 18 | 2 | 0 | 24 | 6 |  |  |  |  | 0
ELV | 136 | 136 | 0 | 136 | 0 | 103 | 6 | 12 | 15 | 0 |  |  |  |  | 0
HSD | 21 | 5 | 0 | 5 | 1 | 0 | 3 | 0 | 1 | 0 |  |  |  |  | 16
PHE | 103 | 103 | 0 | 103 | 0 | 74 | 0 | 25 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 4
AUTOMATION & CONTROL | 301 | 212 | 31 | 181 | 0 | 64 | 58 | 37 | 42 | 11 |  |  |  |  | 89
TELECOM | 125 | 95 | 77 | 18 | 0 | 0 | 67 | 28 | 0 | 0 |  |  |  |  | 30
COMBINED SERVICES | 58 | 9 | 0 | 9 | 0 | 0 | 0 | 9 | 0 | 0 |  |  |  |  | 49
TOTAL | 1341 | 1071 | 108 | 963 | 37 | 546 | 159 | 140 | 137 | 43 |  |  |  |  | 270

## Sheet4
| 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01 | 2028-08-01 | 2028-09-01
Baseline Percentage(%) | 0.02% | 1.44% | 3.38% | 5.04% | 7.15% | 9.5% | 11.83% | 17.52% | 22.31% | 25.06% | 28.36% | 31.67% | 34.46% | 42.23% | 49.51% | 59.56% | 69.34% | 77.68% | 85.3% | 91.39% | 95.11% | 97.22% | 98.34% | 99.1% | 99.64% | 99.91% | 99.96% | 100%
Actual Percentage(%) | 2025-09-01: 0.02%; 2025-10-01: 0.25%; 2025-11-01: 0.69%; 2025-12-01: 1.11%; 2026-01-01: 1.69%; 2026-02-01: 2.29%; 2026-03-01: 3.34%; 2026-04-01: 4.46%; 2026-05-01: 5.19%; 2026-06-01: 6.02%; 2026-07-01: 6.88%; 2026-08-01: 7.6%; 2026-09-01: 7.97%
Remaining Percentage(%) | [12 empty] | 7.97% | 15.88% | 19.09% | 22.32% | 25.51% | 29.19% | 34.15% | 40.14% | 47.34% | 55.88% | 64.65% | 72.19% | 79.55% | 85.91% | 91.04% | 94.02% | 95.93% | 97.23% | 98.27% | 99% | 99.55% | 99.87% | 99.96% | 99.98% | 100%

## Sheet3
Description | Total TDS | Total Submitted to TPL By Micron | Submission to JEG by TPL - Pending - R0 | Submission to JEG by TPL - Pending - R1 | Submission to JEG by TPL - Pending - R2 | Submission to JEG by TPL - Pending - R3 | Submission to JEG by TPL - Pending - R4 | Submission to JEG by TPL - Pending - R5 | Submission to JEG by TPL - Pending - R6 | Submission to JEG by TPL - Submitted | Approved | Percentage Approved | Approved As Noted | Percentage Approved As Noted | In Review with JEG | Revise & Resubmit | Yet to Submit - R0 | Yet to Submit - Revise (R1…)
Electrical | 45 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 37 | 0.82222 | 4 | 0.088889 | 2 | 1 | 1 | 1
HVAC | 43 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 30 | 0.69767 | 6 | 0.13953 | 2 | 3 | 2 | 3
PHE | 62 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 39 | 0.62903 | 2 | 0.032258 | 9 | 2 | 11 | 2
FPS | 37 | 37 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 36 | 35 | 0.94595 | 0 | 0 | 0 | 1 | 0 | 1
ELV | 38 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 31 | 0.81579 | 2 | 0.052632 | 3 | 0 | 2 | 0
HSD | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 16 | 0.57143 | 6 | 0.21429 | 2 | 4 | 0 | 4
BMS | 25 | 25 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 18 | 0.72 | 2 | 0.08 | 4 | 0 | 0 | 0
Telecom | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Total | 308 | 293 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 291 | 236 | 0.76623 | 22 | 0.071429 | 22 | 11 | 16 | 11